## Read Me
iProduce Africa — Access and Open Items Register
Credential-free handover record · Update during the client handover call
Services needing action | Open required items | Developer-managed services | Last reviewed
10 | 9 | 4 | 2026-08-03
How to use this workbook
1. Review every Access Register row with the client administrator. A login does not by itself prove account, billing, or recovery ownership.
2. Record named owners, roles, recovery/2FA location, and a confirmation date. Do not write passwords, recovery codes, secrets, or API keys anywhere in this file.
3. Use individual invitations. Complete password resets and 2FA setup directly in each service or the client’s approved password manager.
4. Track remaining work in Open Items. Update the Status and completion note once evidence exists; do not mark a task complete based on an assumption.
5. GitHub and Vercel are intentionally recorded as developer-managed in the current operational handover. A future technical transfer needs a separate written decision.
6. Save the completed workbook in the client-controlled handover Drive folder and make a dated copy whenever service access changes.
Status definitions
Recorded | Known from the project record; confirm the named person and current recovery/billing details.
Verify | A person, role, login, billing/recovery authority, or 2FA detail still needs confirmation.
Action required | A specific handover action must happen before this service can be treated as ready.
Developer-managed | Operated by the developer under the current support arrangement; not a pending client invitation.
Not started | The service or client-owned property has not yet been set up or verified.

## Access Register
Service Access and Ownership Register
Complete named roles and confirmation dates during the handover call. This workbook contains no credentials.
Service | Purpose | Client role / account holder | Client owner / recovery | Developer role | Billing owner | Credential / 2FA location | Current status | Handover action | Confirmed date | Notes
Sanity CMS | Website editorial content at /admin | Tobi Seun Ajayi — ibotajayi@gmail.com — nominated CMS administrator | Tobi Seun Ajayi — ibotajayi@gmail.com — ownership and recovery authority to confirm | CMS structure and technical support | Client — confirm | Client password manager — verify | Verify | Confirm named administrator, organisation/project authority, billing/recovery, 2FA, and editor invitations. |  | Production dataset is live; editors use individual invitations.
Resend | Operational form email delivery | Client Owner recorded | Named client Owner — verify | Technical configuration support | Client — confirm | Client password manager — verify | Verify | Confirm the named Owner can manage domain, sending, team access, billing, and 2FA. |  | Repository record states the client is the Resend Owner.
Mailchimp | Newsletter subscriptions and campaigns | Client Owner / newsletter administrator — verify | Named client Owner — verify | Newsletter technical support | Client — confirm | Client password manager — verify | Verify | Confirm Owner, team invitations, billing/recovery, audience permissions, and 2FA. |  | Keep subscriber data and campaign ownership client-controlled.
Zoho Mail | Business email and form inboxes | Client administrator | Client email administrator — verify | Initial setup support | Client — confirm | Client password manager — required | Action required | Rotate temporary dev@ and content@ passwords; confirm recovery details and 2FA directly with the client administrator. |  | Never record replacement passwords here.
Domain registrar / DNS | Domain renewal, DNS records, and email routing | Client owner — verify | Tobi Seun Ajayi — ibotajayi@gmail.com — nominated technical contact; registrar/DNS authority to confirm | DNS change support | Client — confirm | Client password manager — verify | Verify | Confirm registrar, DNS-zone administrator, renewal/billing owner, recovery contact, and current website-record TTL. |  | Do not change Zoho/Resend/Mailchimp email records without a controlled review.
Cloudflare Turnstile | Public form bot protection | Developer-managed | Developer-managed | Owns configuration and secret rotation | Developer — confirm | Developer password manager | Developer-managed | Record the support contact; do not expose site secrets in client documents. |  | Current arrangement supplied by developer.
Upstash | Public form rate limiting | Developer-managed | Developer-managed | Owns configuration and secret rotation | Developer — confirm | Developer password manager | Developer-managed | Record the support contact; do not expose credentials in client documents. |  | Current arrangement supplied by developer.
GitHub repository | Website source control | Developer-managed | Developer-managed | Owns repository administration | Developer — confirm | Developer password manager | Developer-managed | No access transfer is implied by this operational handover. Revisit only under separate written technical-transfer scope. |  | Deferred by current handover decision.
Vercel | Website hosting and deployments | Developer-managed | Developer-managed | Owns deployment administration and environment settings | Developer — confirm | Developer password manager | Developer-managed | No access transfer is implied by this operational handover. Revisit only under separate written technical-transfer scope. |  | Deferred by current handover decision.
Google Search Console | Search monitoring and sitemap submission | Client owner — not yet confirmed | Tobi Seun Ajayi — ibotajayi@gmail.com — nominated technical contact; property ownership to confirm | Setup support | Client — confirm | Client password manager — verify | Not started | Create or verify a client-owned property and submit https://iproduceafrica.com/sitemap.xml. |  | Use individual client accounts, not a shared developer login.
Bing Webmaster Tools | Bing search monitoring and sitemap submission | Client owner — not yet confirmed | Tobi Seun Ajayi — ibotajayi@gmail.com — nominated technical contact; property ownership to confirm | Setup support | Client — confirm | Client password manager — verify | Not started | Create or verify a client-owned property and submit the website sitemap. |  | Use individual client accounts, not a shared developer login.
LMS / Netlify | Separate learning platform | Scope and owner — verify | LMS administrator — verify | Website links only; LMS operations are separate | Confirm | Confirm | Verify | Record the LMS owner, hosting/billing role, learner-support contact, and public course URL process. |  | The website does not own learner accounts, enrolment, progress, or certificates.
Figma / asset library | Source design files and approved creative assets | Client owner — verify | Named asset/design administrator — verify | Design handover support | Client — confirm | Client password manager — verify | Verify | Record the approved source links, permissions, and licence/asset ownership where applicable. |  | Only include if such a service is in current use.
Apple / Google developer accounts | Future app-store publishing | Not applicable until app rollout | Future client app owner | Website promotion support only | Client when applicable | Client password manager | Not started | Do not create or share store accounts for website handover unless the mobile-app rollout has approved scope. |  | Required only when official listings are ready.
Google Drive handover folder | Permanent client reference pack | Client owner — confirm | Tobi Seun Ajayi — ibotajayi@gmail.com — nominated technical contact; folder ownership to confirm | Can retain backup only if agreed | Client — confirm | Client password manager / Google Workspace | Verify | Confirm client-controlled folder owner, editors/viewers, and recording/document links. |  | Do not use open-link sharing by default.

## Open Items
Open Items and Evidence Tracker
Keep client obligations separate from developer/shared actions. Close only when the stated evidence exists.
ID | Type | Workstream | Action | Owner | Status | Target date | Complete when | Notes
C-01 | Client | Legal pages | Have client counsel approve or replace the working legal-page copy before treating it as final legal guidance. | Client counsel | Open |  | Approved replacement copy published or written counsel approval recorded. | The current wording is a working baseline, not legal advice.
C-02 | Client | Academy events | Confirm real start dates/times before the six placeholder events are treated as genuine launch content. | Client content lead | Open |  | Verified dates/times entered and published in the CMS. | Do not publish uncertain event details.
C-03 | Client | Zoho security | Rotate temporary dev@ and content@ passwords and confirm recovery details/2FA. | Tobi Seun Ajayi | Open |  | Client-set passwords, individual access, recovery details, and 2FA verified directly. | No passwords in the workbook or meeting recording.
C-04 | Client | LMS/mobile rollout | Approve content, public LMS links, and mobile-app messaging before publishing the rollout to Production. | Client decision-maker | Open |  | Written approval plus reviewed Production content and public links. | Website foundations exist; public rollout is separate.
C-05 | Client | LMS course links | Provide one verified public LMS course URL for each LMS-backed course. | Client LMS owner | Open |  | Each applicable Course record links to a public course page, not a generic login. | The website does not own LMS accounts or learning data.
C-06 | Client | About Story video | Provide an approved YouTube/Vimeo URL if the optional story video will be used. | Client content lead | Optional |  | Approved public/embeddable URL added and checked on About. | No migration required.
C-07 | Client | Store listing assets | Provide official badge artwork only after verified App Store/Google Play listings exist. | Client app owner | Optional |  | Listing is verified and platform-authorised promotional asset is available. | Do not use recreated or unapproved store marks.
D-01 | Developer/shared | Newsletter lifecycle | Record live evidence for unsubscribe, repeat-after-unsubscribe, and hosted rejoin. | Developer / client newsletter owner | Open |  | Recorded end-to-end result for every remaining transition. | Pending-to-subscribed plus source tag is already evidenced.
D-02 | Developer/shared | Search ownership | Create or verify client-owned Google Search Console and Bing properties; submit sitemap. | Tobi Seun Ajayi with website developer support | Open |  | Client ownership recorded and sitemap submitted. | Use the live sitemap URL.
D-03 | Developer/shared | Access register | Confirm every required row with a named owner, recovery/2FA location, billing role, and date. | Tobi Seun Ajayi and website developer | Open |  | No remaining Verify or Action required rows except deliberate developer-managed services. | Complete during the live handover meeting.
D-04 | Developer | Home tablet layout | Resolve the small partner-marquee page-level horizontal overflow around 1024px. | Developer | Open |  | Browser retest at 1024px has no page-level horizontal overflow. | Known issue; unrelated to the LMS/mobile work.
D-05 | Developer/shared | DNS closeout evidence | Verify and record the current website-record TTL and DNS-zone owner after the stable launch window. | Tobi Seun Ajayi with website developer support | Open |  | Current DNS-zone export/screenshot and access owner recorded in this register. | Do not change mail-related records during website DNS work.

## Meeting Checklist
Handover Meeting Checklist
Complete live where possible. Use this as the final meeting record and handover-email attachment.
Meeting action | Owner | Status | Confirmed date | Notes / evidence
Client Drive folder opens for client administrator | Tobi Seun Ajayi | Not started |  | Record the client-controlled folder owner and permission levels.
Nominated CMS editor logs in to /admin | Tobi Seun Ajayi | Not started |  | Use an individual invitation; no shared account.
Client editor publishes a safe CMS change and checks public page | Tobi Seun Ajayi | Not started |  | Record the page URL or record name.
Content Editor Guide and recording chapters shared | Developer | Not started |  | Use short, timestamped recordings or clear chapters.
Access Register reviewed; named owners and roles recorded | Tobi Seun Ajayi + website developer | Not started |  | Do not close rows without recovery/billing/2FA confirmation.
Zoho temporary passwords rotated | Tobi Seun Ajayi | Not started |  | Confirm completion only; never enter passwords.
Remaining open items accepted and owners assigned | Client decision-maker + developer | Not started |  | Attach the dated workbook to the handover email.
Final handover email sent | Website developer | Not started |  | Record the sent date and confirm the folder and recording links are included.

## Lists
Access statuses | Open item statuses | Meeting statuses | Role terms
Recorded | Open | Not started | Client owner
Verify | In progress | In progress | Client administrator
Action required | Waiting on client | Complete | Client editor
Developer-managed | Optional | Not applicable | Developer-managed
Not started | Complete |  | Verify
Complete